## Overview
Issue Management Group on Biodiversity Global and regional level workplan
Result | Indicators | Lead | Timeline | [5 empty] | Link with | Target audience / Users | Timeframe | Budget (2021 - 2022)
|  |  | 2021 |  | 2022
|  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Operationalise the UN Common Approach to Biodiversity at the global and regional levels
Result 1. Awareness raising and knowledge sharing on the UN Common Approach to Biodiversity and continued interagency dialogue and cooperation on the preparation and implementation of the post-2020 global biodiversity framework
Activity 1. Guidance, knowledge products and advocacy materials | E.g., 2 themes per region | UNESCO & FAO (TBC) | [6 empty] | Work with EMG members: Global Divisions and Regional Offices; Secretariats to the UN Decades; Thematic coordination mechanisms | Regional & Country Coordinators, ResReps, Regional Collabaorative Platform, Thematic Coordination, relevant stakeholders | 2030
Activity 1.1. Consult regional offices and DCO on priority themes and formats | bar: 2021 Q3
Activity 1.2. Assign theme leads and issue requests for input | bar: 2021 Q3
Activity 1.3. Review and publish knowledge products as available | bar: 2021 Q4 to 2022 Q4
Activity 1.4. Consult regional offices and DCO on usefulness & knowledge gaps
Activity 2. Access to biodiversity-related knowledge products | Global, regional & thematic opportunities | EMG Secretariat | [6 empty] | UNSDG, Regional Collaborative Platforms, Thematic coordination mechanisms | Regional & Country Offices | 2030 | bar: 2021 Q3 to 2022 Q1
Activity 2.1. Assess platform options for knowledge sharing, e.g. UNSDG knowledge platform, AFP websites, etc. | bar: 2021 Q3
Activity 2.2. Develop a schedule of webinars and communiques to highlight knowledge products | bar: 2021 Q3
Activity 2.3. Collate user feed back on content, format and accessiblity to inform next round | bar: 2021 Q4 to 2022 Q1
Activity 3: Exploring and enhancing collaboration on the post-2020 biodiversity and the pollution agendas | Global, regional & thematic opportunities | UNEP, EMG Secretariat | bar: 2021 Q4 to 2022 Q1
Activity 3.1. 3. Explore and raise awareness on the interlinkages between the post-2020 global biodiversity and beyond 2020 chemicals and waste agenda and articulate guidance for the EMG members to tackle the interconnected crises of biodiversity loss and global pollution through their mandates, initiatives and programmes in an integrated and complementary manner that responds to a system-level approach. | Nexus Dialogue in Oct 2021 | bar: 2021 Q4 to 2022 Q1
Activity 4: Increase awareness and collaboration to deliver on the UN Decade of Ecosystem Restoration | Global, regional & thematic opportunities: raised awareness, increased number of Decade partners among EMG members, new alliances and partnerships, EMG knowledge products | FAO and UNEP (coordinated with UN Decade Coordination Group and Task Forces)
4.1. Nominate activity leads among EMG members | Entities nominations | Individual entities | bar: 2021 Q4
4.2. Develop and maintain living inventory of relevant initiatives, knowledge products and etc. among EMG members (connected to the Decade's inventory) | Developed inventory linked to the Decade inventory | EMG Secretariat, UNEP, FAO and individual entities | bar: 2022 Q1 to 2022 Q4
4.3. Conduct technical webinars/dialogues to raise awareness about the Decade among EMG members | Number of webinars and feedback | FAO, UNEP, EMG Secretariat, UN Decade Coordination Group and Task Forces | bar: 2022 Q1 to 2022 Q4
4.4. Provide relevant inputs for consultaiton with DCO on ecosystem restoration and the development of relevant knowledge product(s) (contribution to Activity 1) | Inputs and knowledge product(s) | UNESCO & FAO (TBC)
4.5. Integrate ecosystem restoration related targets and indicators into QCPR Monitoring Framework and Common Approach reporting framework (contribution to Activities 5 and 6) and Decade implementation monitoring for the GA | Ecosystem restoration indicators are included into QCPR Monitoring Framework and into Common Approach monitoring framework | UNEP & UNDP (TBC)
Result 2. Accountability & global-level reporting within the UN system on its implementation of agreed internal policy to mainstream biodiversity in its programmes and operations
Activity 5. Common Approach indicators for the QCPR Monitoring Framework | 3-5 indicators across policy, programming and operations | Individual entities | [6 empty] | UN INFO, Greening the Blue, Sustainability Strategy Phase I and Phase II | UNGA | 2024
Activity 5.1. Share individual entity inputs and map indicators and potential gaps in reporting on QCPR operational paragraphs related to biodiversity in policy and programming | bar: 2021 Q3 to 2021 Q4
Activity 5.2. Liaise with facilities and operations reporting: assess indicators in collaboration with SUN Team and IMG on Sustainability Management | bar: 2021 Q3 to 2022 Q1
Activity 5.3. Liaise with DCO and UNSDG representatives on UNCT reporting related to indicators at the national level as part of UN INFO | bar: 2021 Q3 to 2021 Q4
Activity 5.4. Promote internally a limited number of measurable targets and related indicators to include in the QCPR monitoring framework | bar: 2021 Q3 to 2021 Q4
Activity 6. Common Approach reporting framework development | Use existing / assess gaps | UNEP & UNDP (TBC) | [6 empty] | UN entities-specific reporting mechanism, CEB/HLCP, QCPR reporting framework | UNGA | 2024
Activity 6.1. Produce an overview of the reporting mechanisms relevant to biodiversity | bar: 2021 Q3 to 2021 Q4
Activity 6.2. Produce a synthesis of existing data availability, baselines and periodicity of submission of reporting | bar: 2021 Q3 to 2022 Q1
Activity 6.3. Produce a reporting framework for the Common Approach to biodiversity | bar: 2021 Q3 to 2022 Q1
Activity 6.4. Report at the global level on collective action on biodiversity to the relevant mechanisms (EMG SOM, CEB/HLCP), as well to the drafting process of the SG’s reports on the QCPR