## Overview
Issue Management Group on Biodiversity Global and regional level workplan
Result/Activity | Indicators | Lead | [5 empty] | Link with | Target audience / Users | Timeframe | Budget (2021 - 2022)
|  |  | 2021 | 2022
|  |  | Q4 | Q1 | Q2 | Q3 | Q4
Operationalise the UN Common Approach to Biodiversity at the global and regional levels
Result 1. Increased awareness and knowledge on the UN Common Approach to Biodiversity and strengthened interagency dialogue and cooperation on the preparation and implementation of the post-2020 global biodiversity framework
Activity 1. Source and update guidance, knowledge products and advocacy materials | E.g., 2 themes per region | UNESCO & FAO (TBC) | [5 empty] | Work with EMG members: Global Divisions and Regional Offices; Secretariats to the UN Decades; Thematic coordination mechanisms | Regional & Country Coordinators, ResReps, Regional Collabaorative Platform, Thematic Coordination, relevant stakeholders | 2030
Activity 1.1. Consult regional mechanisms (ROs, Economic Comissions, etc) and DCO on priority themes, formats, knowledge gaps
Activity 1.2. Assign theme leads and issue requests for input
Activity 1.3. Review and publish knowledge products as available
Activity 2. Increase access to biodiversity-related knowledge products and knowledge | Global, regional & thematic opportunities | EMG Secretariat | [5 empty] | UNSDG, Regional Collaborative Platforms, Thematic coordination mechanisms | Regional & Country Offices | 2030
Activity 2.1. Assess platform options for knowledge sharing, e.g. UNSDG knowledge platform, AFP websites, etc.
Activity 2.2. Conduct webinars, promotional events and develop communiques to highlight knowledge products and share knowledge and lessons learned
Activity 2.3. Collate user feed back on content, format and accessiblity to inform next round
Result 2. Established accountability & global-level reporting within the UN system on implementation of agreed internal policy to mainstream biodiversity in its programmes and operations
Activity 3. Develop Common Approach reporting framework | Use existing / assess gaps | UNEP & UNDP (TBC) | [5 empty] | UN entities-specific reporting mechanism, CEB/HLCP, QCPR reporting framework | UNGA | 2024
Activity 3.1. Produce an overview of the reporting mechanisms relevant to biodiversity
Activity 3.2. Produce a synthesis of existing data availability, baselines and periodicity of submission of reporting
Activity 3.3. Produce a reporting framework for the Common Approach to biodiversity and get it approved by the EMG SOM
Activity 3.4. Report at the global level on collective action on biodiversity to the relevant mechanisms (EMG SOM, CEB/HLCP), as well to the drafting process of the SG’s reports on the QCPR
Result 3. Increased awareness and strengthened collaboration to deliver on the UN Decade of Ecosystem Restoration
Activity 4: Increase awareness and collaboration to deliver on the UN Decade of Ecosystem Restoration | Global, regional & thematic opportunities: raised awareness, increased number of Decade partners among EMG members, new alliances and partnerships, EMG knowledge products | FAO and UNEP (coordinated with UN Decade Coordination Group and Task Forces)
4.1. Nominate activity leads among EMG members | Entities nominations | Individual entities
4.2. Develop and maintain living inventory of relevant initiatives, knowledge products and etc. among EMG members (connected to the Decade's inventory) | Developed inventory linked to the Decade inventory | EMG Secretariat, UNEP, FAO and individual entities
4.3. Conduct technical webinars/dialogues to raise awareness about the Decade among EMG members | Number of webinars and feedback | FAO, UNEP, EMG Secretariat, UN Decade Coordination Group and Task Forces
4.4. Provide relevant inputs for consultaiton with DCO on ecosystem restoration and the development of relevant knowledge product(s) (contribution to Activity 1) | Inputs and knowledge product(s) | UNESCO & FAO (TBC)
4.5. Integrate ecosystem restoration related targets and indicators into QCPR Monitoring Framework and Common Approach reporting framework (contribution to Activities 5 and 6) and Decade implementation monitoring for the GA | Ecosystem restoration indicators are included into QCPR Monitoring Framework and into Common Approach monitoring framework | UNEP & UNDP (TBC)
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: can we shorten this Result to: Established accountability & global-level reporting within the UN system on implementation of the Common Approach?
Note on A22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: can we shorten this Result to: Established accountability & global-level reporting within the UN system on implementation of the Common Approach?